## Sheet1
[9 empty] | October | [30 empty] | November
[9 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
PAGE/ACTIVITY | Task | DESCRIPTION OF WORK | NAME | START DATE | END DATE | HOURS | % DONE | WORK DAYS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29\ | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
[9 empty] | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Search Recipe | Test Retrofit API | Install and test Retrofit API, Creat Interface for one API, Call API and get Response | Thiago Lyra | 2023-09-29 | 2023-10-01 | 6 | 100% | bar: Week 1 1 S
Search Recipe | Create Main Classes and convert Json to Object | Install GSON Converter Create all Classes related to recipes. Recipe, Ingredients, etc.. | Thiago Lyra | 2023-10-02 | 2023-10-19 | 4 | 100% | bar: Week 1 1 S to Week 3 19 T
Search Recipe | Create Layout | Create Layout and organize activity Layout | Thiago Lyra | 2023-10-02 | 2023-10-03 | 1 | 100% | bar: Week 1 1 S to Week 1 2 M
Search Recipe | Create ListView Adapter | Create ListView Adapter to control the List View Item | Thiago Lyra | 2023-10-03 | 2023-10-13 | 1 | 100% | bar: Week 1 3 T to Week 2 13 F
Search Recipe | Create Page Logic Control | Create Logic to call the API, Button Handlers, List View Updates | Thiago Lyra | 2023-10-13 | 2023-10-19 | 5 | 100% | bar: Week 2 13 F to Week 3 19 T
Recipe Details | Create Layout | Create Layout and organize activity Layout | Thiago Lyra | 2023-10-19 | 2023-10-19 | 1 | 100% | bar: Week 3 19 T
Recipe Details | New Endpoint API | Add new endpoint interfaces | Thiago Lyra | 2023-10-19 | 2023-10-19 | 2 | 100% | bar: Week 3 19 T
Recipe Details | Create Activity Logic | Create Logic to call the API, Button Handlers, List View Updates | Thiago Lyra | 2023-10-19 | 2023-10-19 | 2 | 100% | bar: Week 3 19 T
Recipe Details | Fix bug and errors | Fix crashes, update layout, adding HTML Reader | Thiago Lyra | 2023-10-31 | 2023-10-31 | 5 | 100% | bar: Week 1 31 T
My Recipe | Create Layout | Create Layout and organize activity Layout | Thiago Lyra | 2023-10-31 | 2023-10-31 | 1 | 100% | bar: Week 1 31 T
My Recipe | Create ListView Adapter | Create Recycler View Adapter class to manage the recycler view item | Thiago Lyra | 2023-10-31 | 2023-10-31 | 1 | 100% | bar: Week 1 31 T
My Recipe | Create Page Logic Control | Create Handlers, item click listener | Thiago Lyra | 2023-10-31 | 2023-10-31 | 1 | 100% | bar: Week 1 31 T
My Recipe | Fix bug and errors | Fix crashes, update layout, correct bugs | Thiago Lyra | 2023-10-31 | 2023-10-31 | 3 | 100% | bar: Week 1 31 T
My Recipe | Adding Database Controller | Add and install SQLight Server, Create table method and Query Methods(Select all recipe and Select Single Recipe) | Thiago Lyra | 2023-11-06 | 2023-11-06 | 2 | 100% | bar: Week 2 6 M
My Recipe | Implement Database logic in My Recipe Activity | Create Method to call and parse the data to Recycler view controller | Thiago Lyra | 2023-11-06 | 2023-11-06 | 2 | 100% | bar: Week 2 6 M
My Recipe | Updating Recycler View and Fix bugs | Fixing bugs to control recycler view and correct the Item Click listener that wasn't working | Thiago Lyra | 2023-11-08 | 2023-11-08 | 2 | 100% | bar: Week 2 8 W
My Recipe | Improve Layout | Improve Layout of My Recype, add AI generated Images and organize structure | Thiago Lyra | 2023-11-08 | 2023-11-08 | 4 | 100% | bar: Week 2 8 W
Add Recipe | Create Layout | Create Layout and organize activity Layout | Thiago Lyra | 2023-11-08 | 2023-11-08 | 1 | 100% | bar: Week 2 8 W
Add Recipe | Create Page Logic Control | Create Handlers, item click listener | Thiago Lyra | 2023-11-08 | 2023-11-08 | 1 | 100% | bar: Week 2 8 W
Add Recipe | Improve Layout | Improve Layout of Add Recype, add AI generated Images and organize structure | Thiago Lyra | 2023-11-08 | 2023-11-08 | 1 | 100% | bar: Week 2 8 W

## Sheet2
Name | Type of PAGE/ACTIVITY
Dilan Temel | login
Jaycee Kim | profile
Thiago Lyra | Add Recipe
Project Planning
My Recipe
Search Recipe
Recipe Details